## Trang tính1
EPIC | Screen/Function | Iteration 1 | Iteration 2 | Iteration 3 | Description | In charge | RDS | Status | Line of code | Note/Update
Epic 1: Authentication | User Login | TRUE | FALSE | TRUE | As a Registered User, I want to log in to the system so that I can access the features authorized for my role. | QuangLN |  | Done | 45 | Level 1 (3 field) , include username, password, button logout(75%) -> LOC = 60 * 75% = 45
| User Logout | TRUE | FALSE | FALSE | As a Registered User , I want to logout the website so that I can protect my personal information and account security, especially when using a public device. | QuangLN |  | Done
| User Register | TRUE | TRUE | FALSE | As a new user, I want to register an account using my email and password So that I can access the system and use its features | QuangLN |  | Done | 67.5 | Level 2 (6 field), include fullname, phone_number, username, email, password, confimr pasword 75% quality -> LOC = 90 * 75% = 67.5
EPIC 2: Product Discovery | View homepage | TRUE | FALSE | TRUE | As a Guest, I want to view the homepage so that I can see featured books and navigate to other sections of the store. | QuangLN |  | Done | 90 | Level 3 (4 times access to database), 75% quality => LOC = 120 * 75% = 90
| View Product Detail | TRUE | TRUE | TRUE | As a Guest, I want to view detailed information about a specific book so that I can understand its content, price, and specifications before deciding to add it to my cart. | TrungNC, QuangLN |  | Done | TrungNC : 75 | TrungNC: Level 4 (7 field), include: title, author, price, description, imageUrl, stock selection, addToCart. 2 times access database. 50% quality => LOC = 150 * 50% = 75
| Filter Search | FALSE | TRUE | FALSE | As a registered user, I want to search and filter items in the inventory So that I can quickly find the products I need | QuangLN |  | Done | 90 | Level 3 (8 fields) include: price, type of book, sort, author, publisher, supplier, btn approve filter, btn delete filter 75% -> LOC = 120 * 75% = 90
| Search Product | TRUE | FALSE | FALSE | As a Guest, I want to search for books by entering keywords (title or author) into the search bar so that I can quickly find the specific products I am interested in without browsing through all categories. | HoangNV |  | Done | 90 | 8 field: search, book list, price, author, publisher, sorting, btn filter, delete filter -> LOC = 120 * 75% = 90
EPIC 3: Admin Supervision | Admin Search Scope | TRUE | FALSE | FALSE | As an Admin, I want to search for products on the public website including hidden or out-of-stock items, so that I can verify their display settings without going into the backend database. | TrungNC |  | Done | 67.5 | Level 2(4 field, 1 time access to database). 75% quality -> LOC = 90 * 75% = 67.5
| Admin Toolbar & Overlay | TRUE | FALSE | FALSE | As an Admin, I want to see a management toolbar overlay when browsing the public homepage, so that I can quickly switch to the Dashboard or identify that I am browsing in "Admin Mode". | TrungNC |  | Done | 45 | 2 field, 75% quality -> LOC = 60 *75% = 45
EPIC 4: Warehouse Inventory Management
| Product Quick Inspection | FALSE | FALSE | FALSE | As an Admin, I want to view "Internal Data" (such as Import Price, Supplier) directly on the Product Detail page and have a "Quick Edit" button, so that I can spot pricing errors and fix them immediately. | TrungNC |  | Done | 90 | Level5 (12 field), include: title, author, price, description, imageUrl, stock selection, addToCart, stockQuantity, importPrice, active, publisher, quickEdit. 2 times access database. 50% quality -> LOC = 180 * 50% = 90
| View Inventory List | TRUE | TRUE | FALSE | As a Warehouse staff , I want to view and search the inventory list so that I can monitor the stock levels and status of all books in the warehouse. | DongTD |  | Done | 120 | 17 fields, include: id, title, category, shelfLocation, author, publisher, price, stockQuantity, status, keyword, categoryFilter, authorFilter, publisherFilter, filterButton, clearFilterButton, showEntries, pagination. 1 times access database. 50% quality. => LOC = 240 * 50% = 120
| View Low Stock Book | FALSE | TRUE | FALSE | As a warehouse staff, I want to view low-stock books so that I can restock them in time. | DongTD |  | Done | 90 | 11 fields, include: backButton, restockButton, showEntries, id, title, category, publisher, currentStock, level, searchBox, pagination. 1 time access database. 50% quality => LOC = 180 * 50% = 90
| Supplier/Vendor Management | FALSE | TRUE | FALSE | As a warehouse staff, I want to manage suppliers/vendors so that I can easily handle book purchasing and restocking. | DongTD |  | Done | 180 | 20 fields, include: backButton, addButton, showEntries, searchBox, stt, supplierName, contactPerson, phone, email, address, editButton, deleteButton, pagination, modalSupplierName, modalContactPerson, modalPhone, modalEmail, modalAddress, saveButton, cancelButton. 5 times access database. 75% quality. => LOC = 240 * 75% = 180
| Warehouse Location Setup | FALSE | TRUE | FALSE | As a warehouse staff, I want to set up warehouse locations so that books are stored and retrieved efficiently. | DongTD |  | Done | 180 | 21 fields, include: backButton, addLocationButton, showEntries, searchBox, stt, locationCode, zone, shelf, floor, categoryAssigned, note, editButton, deleteButton, pagination, modalZone, modalShelf, modalFloor, modalCategory, modalNote, saveButton, cancelButton. 5 times access database, 75% quality. => LOC = 240 * 75% = 180
| WareHouse Dashboard | TRUE | TRUE | TRUE | As a warehouse Keeper, I want to view a warehouse dashboard with key inventory information, So that I can quickly monitor stock status and make operational decisions | DongTD |  | On Going
| View Purchase Orders | FALSE | FALSE | TRUE | As a Warehouse staff, I want to view approved purchase orders created by Buyer or Admin Business so that I only receive goods based on valid and authorized PO. | DongTD |  | To Do
| Issue Goods | FALSE | FALSE | TRUE | As a Warehouse staff, I want to issue goods based on approved sales orders from Customer or Buyer so that stock is deducted correctly and legally. | DongTD |  | To Do
| Receive Goods | FALSE | FALSE | TRUE | As a Warehouse staff, I want to receive goods based on approved purchase orders from Admin Business or approved return orders so that inventory is updated accurately. | DongTD |  | To Do
EPIC 5: User management |  | FALSE | FALSE | FALSE
| View User profile | FALSE | TRUE | FALSE | As a registered user, I want to view my profile so that I can view my information | QuangLN |  | Done | 67.5 | 1 time access to database, 75%
| Change password | FALSE | TRUE | FALSE | As a registered user, I want to change my password so that I can improve account's security | QuangLN |  | Done |  | 3 field include curent password, new password, confirm new password, 75%
| Edit Profile | FALSE | TRUE | TRUE | As a registered user, I want to edit my profile so that I can update my personal information | QuangLN |  | Done |  | 1 fiield, include change email, 75%
EPIC 6: Admin Dashboard & Management | Product Catalog Management | FALSE | TRUE | FALSE | As an Admin, I want a paginated and sortable product table with status indicators, so that I can manage thousands of books efficiently and quickly identify items that are hidden or low in stock.As an Admin, I want a paginated and sortable product table with status indicators, so that I can manage thousands of books efficiently and quickly identify items that are hidden or low in stock. | TrungNC |  | Done | 120 | Level 7 (14 field, 2 times access to database): add category, add new book, search bar, filter dropdown, search button, book Id, image, book detail, category, price, stock, status, edit, delete. 50% quality. => LOC = 240 * 50% = 120
| Order Processing | FALSE | TRUE | FALSE | As an Admin, I want a "Smart Search" bar and date filters for orders, so that I can instantly locate a transaction using only a partial ID, customer name, or phone number. | TrungNC |  | Done | 120 | Level 7(11 field, 3 time access the database) search bar, 2 date pickers, status dropdown, filter button, order Id, customer, order date, total amount, status, action. 50% quality => LOC = 240 * 50% = 120
| User Administration | FALSE | TRUE | FALSE | As an Admin, I want to filter users by their specific Role (Admin/Customer/Warehouse/Staff) and Status, so that I can audit staff accounts or ban violative customers. | TrungNC |  | Done | 120 | 10 field: create new user, search bar, roles dropdown, ID, user info, contact, role, status, ban user, join date. 2 times access the database. 50% quality => LOC = 240 * 50% =120
EPIC 7: Sale Staff | Order Management | FALSE | TRUE | FALSE | As a Sale Staff, I want to view a list of all orders. So that I can easily monitor incoming orders and prioritize which ones need to be processed first. | LocND |  | Done | 120 | 8 field:date, customer's name,phone,address,price,status,action: update and view detail, 4 time access database, 50% quality
| View Order Details | FALSE | TRUE | FALSE | As a Sale Staff,I want to view the full details of a specific order.So that I can verify the customer's information, the ordered books, and the payment status before making a decision to confirm or cancel it. | LocND |  | Done | 105 | 8 fields:customer's name,phone,address,,date,status,img,book's name, price,quantity, action:back to order dashboard,3 time access database,50% quantity.
| Update Order | FALSE | TRUE | FALSE | As a Sale Staff,I want to update the processing status and payment status of an order, So that the workflow can proceed to the warehouse for packaging or reflect the actual state of the transaction. | LocND |  | Done | 90 | 8 fields include: date, customer's name, phone, address, price, status, action: back to order dashboard and save,2 time access database ,50% quality
| Review Management | FALSE | TRUE | FALSE | "As a Sale Staff, I want to view a list of all product reviews and filter them by star rating (1 to 5 stars). So that I can monitor customer satisfaction and directly contact them via email to resolve bad experiences or express gratitude. | HoangNV |  | Done | 135 | 9 fields: username, email, title ,review_id, user_id, book_id, rating, comment, create_at, 75% quality -> LOC = 180 * 75% = 135
| Customer Support | TRUE | TRUE | FALSE | As a Sale Staff, I want to view the customer list and search for specific customers by their name, email, or phone number. So that I can quickly find their contact information and send them support emails to resolve order-related issues. | HoangNV |  | Done | 120 | 10 fields: user_id, username, password, email, fullname, phone_number, address, role, status, create_at, 75% quality -> LOC = 160 * 75% = 120
EPIC 8: Sales & Performance Reporting | Visual Sales Dashboard | FALSE | TRUE | FALSE | As an Admin, I want to view a graphical representation of revenue and order volume over time (e.g., last 7 days, this month), so that I can instantly spot sales trends without calculating them manually from the Order table. | TrungNC |  | Done | 45 | 4 fields: date, price, explaination, graph. 1 time access to database. 50% quality => LOC = 90 * 50% = 45
| Order Status Distribution | FALSE | TRUE | FALSE | As an Admin, I want to see a breakdown of order statuses (Pending vs. Completed vs. Cancelled), so that I can assess the efficiency of my fulfillment process (e.g., "Are too many orders being cancelled?"). | TrungNC |  | Done | 45 | 5 fields: pending, shipping, cancelled, completed, pie chart. 1 time access to database. 50% quality => LOC = 90 * 50% =45
EPIC 9: Cart Management | Add To Cart | TRUE | FALSE | FALSE | As a Customer, I want to click the "Add to Cart" button on the book detail or list page so that I can save the book I intend to purchase. | LocND |  | Done | 30 | 1 field: add to cart button,1 times access database,50 % quality
| Add To Cart | FALSE | FALSE | TRUE | As a Customer, I want to see the "Add to Cart" button disabled and displaying "Out of Stock" if the stock is 0 so that I do not waste time trying to order an unavailable item.
| Header (Mini-Cart) | FALSE | FALSE | TRUE | As a Customer, I want to hover over the Cart icon on the header to see a mini-cart with my added books so that I can quickly check my cart without leaving the current page.
| Update/Remove Cart | TRUE | FALSE | FALSE | As a Customer,I want to increase/decrease quantity or remove items so that I can finalize the exact number of itemsI want to buy. | LocND |  | Done | 135 | 7 field:image, tittle,price,quantity, back to shop button , continue shopping button, checkout button,3 time access database, 75%quality
| View Cart Page | TRUE | FALSE | FALSE | As a Buyer, I want to view my cart so that I can review the items selected and see the total cost. |  |  | Done
EPIC 10: Checkout Initiation | Auth Modal / Checkout | FALSE | FALSE | TRUE | As an Unregistered Customer, I want to see options to "Log in", "Register", or "Checkout as Guest" when proceeding to checkout so that I can choose the most convenient way to complete my purchase.
| Checkout Page | FALSE | FALSE | TRUE | As a Registered Customer, I want to have my full name, phone number, and default shipping address automatically filled in so that I can save time typing.
| Checkout Page | FALSE | TRUE | FALSE | As a Customer, I want to have a clear form to enter the recipient's information (Name, Phone, City, District) so that the delivery staff knows exactly where to ship my books. | LocND |  | Done | 60 | 6 fields include:name,phone,address,method of payment,button " xác nhận thanh toán", button" quay lại giỏ hàng",1 time access database,50%quality
EPIC 11: Promo & Payment | Checkout Page | FALSE | FALSE | TRUE | As a Customer, I want to enter a promo code (voucher) and click "Apply" so that the system automatically deducts the discount amount from my total bill. |  |  | To Do
| Checkout Page | FALSE | FALSE | TRUE | As a Customer, I want to see the shipping fee automatically calculated and displayed based on my address so that I know the exact final amount I need to pay. |  |  | To Do
| Checkout Page | FALSE | FALSE | TRUE | As a Customer, I want to choose between "Cash on Delivery (COD)" and "Online Payment (VNPay/MoMo)" so that I can pay using the method that suits my current preference. |  |  | To Do
| Checkout Page | FALSE | FALSE | TRUE | As a Customer, I want to see an order summary (books, subtotal, shipping fee, discount, total) before confirming so that I can verify all information is correct. |  |  | To Do
EPIC 12: Post-Checkout | System / Backend | FALSE | FALSE | TRUE | As a Store Owner, I want to have the system immediately deduct the purchased quantity from the inventory so that I avoid overselling out-of-stock books to subsequent customers. |  |  | To Do
| System / Backend | FALSE | FALSE | TRUE | As a Customer, I want to have my shopping cart automatically cleared after a successful order so that I can start a fresh shopping session next time. |  |  | To Do
| Checkout Success Page | FALSE | FALSE | TRUE | As a Customer, I want to see a "Checkout Successful" screen displaying my Order ID so that I know my transaction went through and I can use the ID for future tracking. |  |  | To Do
EPIC 13: Order Tracking | My Orders Page | FALSE | FALSE | TRUE | As a Registered Customer, I want to access the "My Orders" section to view the current status of my order (Pending, Shipping...) so that I know when my books will arrive. |  |  | To Do
| Order Detail Page | FALSE | FALSE | TRUE | As a Customer, I want to cancel my order and provide a reason, but only while the order is in "Pending" status so that I can correct mistakes without causing shipping losses for the bookstore. |  |  | To Do
| Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to see new orders appear immediately on the management dashboard so that I can quickly assign warehouse staff to pack and ship the books. |  |  | To Do
EPIC 14: Return Eligibility | Order Detail Page | FALSE | FALSE | TRUE | As a System, I want to automatically hide the "Request Return" button if the order was delivered more than 7 days ago so that the store's return policy time limit is strictly enforced. |  |  | To Do
| Order Detail Page | FALSE | FALSE | TRUE | As a System, I want to prevent customers from requesting returns for digital products (e.g., Ebooks, Audiobooks) so that intellectual property is protected from abuse. |  |  | To Do
EPIC 15: Advanced Return Request | Return Form | FALSE | FALSE | TRUE | As a Customer, I want to choose my preferred return logistics method (e.g., "Drop off at Post Office" vs. "Shipper picks up at my address") so that the return process is convenient for my schedule. |  |  | To Do
| Return Form | FALSE | FALSE | TRUE | As a Customer, I want to choose how I receive my refund (e.g., "Store Credit/Voucher" vs. "Original Payment Method") so that I have flexibility in managing my money. |  |  | To Do
| Return Status Page | FALSE | FALSE | TRUE | As a Customer, I want to be able to cancel my own Return Request if it is still in "Pending Review" status so that I can keep the book if I change my mind. |  |  | To Do
EPIC 16: Admin Processing & QC | Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to change the status to "Action Required" and request the customer to provide clearer photos so that I can accurately assess the damage before approving the return. |  |  | To Do
| Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to explicitly reject a return request and provide a mandatory reason (e.g., "Book damaged by user", "Past return window") so that the decision is transparent to the customer. |  |  | To Do
| System / Backend | FALSE | FALSE | TRUE | As a System, I want to automatically email the customer the exact reason if their return request is rejected so that they are informed without needing to contact customer support. |  |  | To Do
| Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to perform a Quality Control (QC) check when the physical book arrives at the warehouse and mark it as "Passed QC" or "Failed QC" so that I only refund valid returns. |  |  | To Do
EPIC 17: Advanced Refund & Restock | Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to have the option to issue a "Partial Refund" (e.g., refunding 80% because the book jacket is missing) so that the store does not take a full loss on incomplete returns. |  |  | To Do
| System / Backend | FALSE | FALSE | TRUE | As a System, I want to automatically generate and email a Discount Voucher to the customer if they selected "Store Credit" for their refund so that the money stays within the bookstore's ecosystem. |  |  | To Do
| System / Backend | FALSE | FALSE | TRUE | As a System, I want to NOT add the returned book back to stock_quantity if the Admin marked it as "Failed QC / Unsellable" so that damaged goods are not accidentally sold to the next customer. |  |  | To Do
EPIC 18: Notifications & Exceptions | Email System | FALSE | FALSE | TRUE | As a Customer, I want to receive automatic email updates at every major step of the return process (Approved, Item Received, Refund Issued) so that I don't have to constantly check the website. |  |  | To Do
| System / Backend | FALSE | FALSE | TRUE | As a System, I want to automatically cancel an approved return request if the customer does not hand over the book to the shipping carrier within 5 days so that pending returns do not stay in the system forever. |  |  | To Do
| Admin Dashboard | FALSE | FALSE | TRUE | As an Admin, I want to view a monthly report of "Top Returned Books" and their return reasons so that I can identify products with chronic quality issues from the publisher. |  |  | To Do